## Feb 2025 01-15
Project Leader: Mikel Cox |  | Project: Z2 Educational Video Player | [15 empty] | Date: 02/14/25
Project Objective: Create a video sharing website |  | Project Team: Logan Z, Hunter, Mikel, Ashton, Zach
| Major Tasks | Project Completed By: date | [11 empty] | Owner / Priority
1 | Video Player Customization | ˜ |  |  | ˜ |  |  |  | ™ |  |  |  |  | ˜ | ˜ |  | ˜
2 | Page Layout | ˜ | ˜ | [8 empty] | ™ |  |  | ˜ |  | ˜
3 | Page Banner | ˜ | ˜ | [6 empty] | ™ |  |  |  |  | ˜
4 | Database for acounts |  |  | ˜ |  | ˜ |  |  |  | ™ | [5 empty] | ˜
5 | Accounts/Login Page |  |  |  | ˜ | [5 empty] | ™ | [5 empty] | ˜
6 | Minor functionality of separate tabs | [6 empty] | ™ | ™ |  |  |  |  | ˜ | ˜ |  | ˜
7 | Categories (Subjects + Searching) |  |  |  | ˜ |  | ™ |  | ™
8 | Flesh out navigation |  |  |  |  | ˜ | [5 empty] | ™ |  | ˜ | ˜ | ˜ | ˜ | ˜
9 | Video Uploading | [5 empty] | ˜ | ˜ | ˜ | ™ | [7 empty] | ˜
10 | Login Session | [5 empty] | ™ | ™ | ˜ |  |  |  | ™ |  |  | ˜
11 | Password Hashing | [6 empty] | ˜ | [9 empty] | ˜
12 | [6 empty] | ˜
13
14
15
16
17
18
19
20
|  | Oct 1-15 | Oct 16-31 | Nov 1-15 | Nov 16-30 | Dec 1-15 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Feb 16-28 | Mar 1-15 | Mar 16-30 | Apr 1-15 | Ashton | Hunter | Mikel | Logan Z | Zach
Video uploading accepts mp4's, can easily expand to accept other formats (Zach). Basic session allows persistent login, though session seems "too" persistent right now (Mikel).
Video player undergoing visual changes to be more appealing to the eye and have an easier-to-follow layout (Hunter). Sessions allow profile page to be designed (Ashton).
Login and registration pages undergoing visual changes (Logan). We need to discuss how we want to categorize video uploads and into what categories, but it's simple to implement.
I hope to have our site outward-facing and publicly accessible from anywhere on the Internet by the end of the semester. I think we can accomplish that.
|  |  | Alt + | 152 | 153
|  |  | Wingdings 2 | ˜ | ™
Major Tasks
Summary & Forecast
Target Dates

## Feb 2025 16-28
Project Leader: Mikel Cox |  | Project: Z2 Educational Video Player | [15 empty] | Date: 02/28/25
Project Objective: Create a video sharing website |  | Project Team: Logan Z, Hunter, Mikel, Ashton, Zach
| Major Tasks | Project Completed By: date | [11 empty] | Owner / Priority
1 | Video Player Customization | ˜ |  |  | ˜ |  |  |  | ™ |  |  |  |  | ˜ | ˜ |  | ˜
2 | Page Layout | ˜ | ˜ | [6 empty] | ™ | ™ | ™ |  |  | ˜ |  | ˜
3 | Page Banner | ˜ | ˜ | [6 empty] | ™ |  |  |  |  | ˜
4 | Databases |  |  | ˜ |  | ˜ |  |  |  | ™ | ™ | ™ |  |  |  | ˜
4.1 | Comments table | [8 empty] | ™ | ™ | ™
4.2 | Likes/dislikes | [8 empty] | ™ | ™ | ™
4.3 | Categories (Subjects + Searching) |  |  |  | ˜ |  | ™ |  | ™ | ™ | ™ | ™
5 | Accounts/Profile/Login Page |  |  |  | ˜ |  |  |  |  | ˜ | ™ | [5 empty] | ˜
6 | Minor functionality of separate tabs | [6 empty] | ™ | ™ |  |  |  |  | ˜ | ˜ |  | ˜
7 | Flesh out navigation |  |  |  |  | ˜ | [5 empty] | ™ |  | ˜ | ˜ | ˜ | ˜ | ˜
8 | Video Uploading | [5 empty] | ˜ | ˜ | ˜ | ™ | [7 empty] | ˜
9 | Login Session | [5 empty] | ™ | ™ | ˜ |  |  |  | ™ |  |  | ˜
10 | Password Hashing | [6 empty] | ˜ | [9 empty] | ˜
11 | Hosting/Domain for Internet access | [8 empty] | ™ | ™ | ™ | ™ | ˜ | ˜ | ˜ | ˜ | ˜
12
13
14
15
16
17
|  | Oct 1-15 | Oct 16-31 | Nov 1-15 | Nov 16-30 | Dec 1-15 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Feb 16-28 | Mar 1-15 | Mar 16-30 | Apr 1-15 | Ashton | Hunter | Mikel | Logan Z | Zach
Improvements to UI background for easier viewing (Hunter). Began implementing basic functionality of the the profile page (Ashton).
Still need to expand video uploading to upload other formats (Zach). Still tweaking various UI elements (Logan). Researching how to get website hosted for public access (Mikel).
We're stalled a little bit, not sure where to go next with the project until the databases are set up properly. There's a minor bug with the sessions, session not activated if login not
accessed from the index.html page. It's about time to find a way to get the site outward-facing to the Internet, instead of just being a local network app.
|  |  | Alt + | 152 | 153
|  |  | Wingdings 2 | ˜ | ™
Major Tasks
Summary & Forecast
Target Dates

## Mar 2025 01-21
Project Leader: Mikel Cox |  | Project: Z2 Educational Video Player | [15 empty] | Date: 02/28/25
Project Objective: Create a video sharing website |  | Project Team: Logan Z, Hunter, Mikel, Ashton, Zach
| Major Tasks | Project Completed By: date | [11 empty] | Owner / Priority
1 | Video Player Customization | ˜ |  |  | ˜ |  |  |  | ™ |  |  |  |  | ˜ | ˜ |  | ˜
2 | Page Layout | ˜ | ˜ | [6 empty] | ™ | ™ | ™ |  |  | ˜ |  | ˜
3 | Page Banner | ˜ | ˜ | [6 empty] | ™ |  |  |  |  | ˜
4 | Databases |  |  | ˜ |  | ˜ |  |  |  | ™ | ˜ | ™ |  |  |  | ˜
4.1 | Comments table | [8 empty] | ™ | ˜ | ™
4.2 | Likes/dislikes | [8 empty] | ™ | ˜ | ™
4.3 | Categories (Subjects + Searching) |  |  |  | ˜ |  | ™ |  | ™ | ™ | ˜ | ™
5 | Accounts/Profile/Login Page |  |  |  | ˜ |  |  |  |  | ˜ | ˜ | [5 empty] | ˜
6 | Minor functionality of separate tabs | [6 empty] | ™ | ™ |  |  |  |  | ˜ | ˜ |  | ˜
7 | Flesh out navigation |  |  |  |  | ˜ | [5 empty] | ™ |  | ˜ | ˜ | ˜ | ˜ | ˜
8 | Video Uploading | [5 empty] | ˜ | ˜ | ˜ | ˜ | [7 empty] | ˜
9 | Login Session | [5 empty] | ™ | ™ | ˜ |  |  |  | ™ |  |  | ˜
10 | Password Hashing | [6 empty] | ˜ | [9 empty] | ˜
11 | Hosting/Domain for Internet access | [8 empty] | ™ | ™ | ™ | ™ | ˜ | ˜ | ˜ | ˜ | ˜
12 | API | [9 empty] | ™ | ™ | ™ |  |  | ˜
13 | Dockerization | [9 empty] | ™ | ™ | ™ | ˜ | ˜ | ˜ | ˜ | ˜
14
15
16
17
|  | Oct 1-15 | Oct 16-31 | Nov 1-15 | Nov 16-30 | Dec 1-15 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Feb 16-28 | Mar 1-15 | Mar 16-30 | Apr 1-15 | Ashton | Hunter | Mikel | Logan Z | Zach
Spent spring break attempting to design an API (Mikel).
I honestly don't know what everyone else did. I didn't really ask them to do anything, they've been waiting on me to finish the API so they can use it to frontend work.
I'm not a good project manager. I'm not good at anything.
|  |  | Alt + | 152 | 153
|  |  | Wingdings 2 | ˜ | ™
Major Tasks
Summary & Forecast
Target Dates