## Feb 2025 01-15
Project Leader: Mikel Cox |  | Project: Z2 Educational Video Player | [15 empty] | Date: 02/14/25
Project Objective: Create a video sharing website |  | Project Team: Logan Z, Hunter, Mikel, Ashton, Zach
| Major Tasks | Project Completed By: date | [11 empty] | Owner / Priority
1 | Video Player Customization | ˜ |  |  | ˜ |  |  |  | ™ |  |  |  |  | ˜ | ˜ |  | ˜
2 | Page Layout | ˜ | ˜ | [8 empty] | ™ |  |  | ˜ |  | ˜
3 | Page Banner | ˜ | ˜ | [6 empty] | ™ |  |  |  |  | ˜
4 | Database for acounts |  |  | ˜ |  | ˜ |  |  |  | ™ | [5 empty] | ˜
5 | Accounts/Login Page |  |  |  | ˜ | [5 empty] | ™ | [5 empty] | ˜
6 | Minor functionality of separate tabs | [6 empty] | ™ | ™ |  |  |  |  | ˜ | ˜ |  | ˜
7 | Categories (Subjects + Searching) |  |  |  | ˜ |  | ™ |  | ™
8 | Flesh out navigation |  |  |  |  | ˜ | [5 empty] | ™ |  | ˜ | ˜ | ˜ | ˜ | ˜
9 | Video Uploading | [5 empty] | ˜ | ˜ | ˜ | ™ | [7 empty] | ˜
10 | Login Session | [5 empty] | ™ | ™ | ˜ |  |  |  | ™ |  |  | ˜
11 | Password Hashing | [6 empty] | ˜ | [9 empty] | ˜
12 | [6 empty] | ˜
13
14
15
16
17
18
19
20
|  | Oct 1-15 | Oct 16-31 | Nov 1-15 | Nov 16-30 | Dec 1-15 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Feb 16-28 | Mar 1-15 | Mar 16-30 | Apr 1-15 | Ashton | Hunter | Mikel | Logan Z | Zach
Video uploading accepts mp4's, can easily expand to accept other formats (Zach). Basic session allows persistent login, though session seems "too" persistent right now (Mikel).
Video player undergoing visual changes to be more appealing to the eye and have an easier-to-follow layout (Hunter). Sessions allow profile page to be designed (Ashton).
Login and registration pages undergoing visual changes (Logan). We need to discuss how we want to categorize video uploads and into what categories, but it's simple to implement.
I hope to have our site outward-facing and publicly accessible from anywhere on the Internet by the end of the semester. I think we can accomplish that.
|  |  | Alt + | 152 | 153
|  |  | Wingdings 2 | ˜ | ™
Major Tasks
Summary & Forecast
Target Dates